## Version History
Project Information
Project:
Client:
Start Date:
Team: | <<Member 1, Member 2, Member 3, ...>>
Date | Description | Version | Author | Reviewer
2016-08-28 | Initial Version | 1 | Janakiram | Sunil
Note:
** Purpose: The purpose of clarification log is to clarify the requirements with the customer, as recorded in the Business Requirements Document (BRD).

## Product Backlog
Product Backlog
User Story ID | Project | Business Process Title | User Stories | Priority | Sprint Details | Owner | Status
USID1 | Mortgage loan processing System | Non-registered User Inquire | As a non-registered user,I want to inquire for mortgage loan process,So that I can apply for a mortgage loan | 1 | 1
USID2 | Mortgage loan processing System | Non-Registerd User Signup | As a non-registered user,I want to sign up for mortgage loan process,So that I can apply for a mortgage loan | 1 | 1
USID3 | Mortgage loan processing System | Resistered User Login | As a registered user,I want to login to the system,so that I can apply mortgage loan | 1 | 1
USID4 | Mortgage loan processing System | Registered User Functionality | As a registered user,I want to check my loan status,so that I can know my loan request is accepted or not | 1 | 1
USID5 | Mortgage loan processing System | Registered User Functionality | As a registered user,I want to know how much loan amount is sanctioned/status also | 2 | 1
USID6 | Mortgage loan processing System | Registered User Functionality | As a registered user, I want to know how to change my passowrd in emergency | 1 | 1
USID7 | Mortgage loan processing System | Verifying/Assigning a Inspector | As a Mortgage Loan officer, I want to log in to the system,so that I can verify the documents provided by the user | 1 | 2
USID8 | Mortgage loan processing System | Property Inspection | As a Loan Inspector,I want to login to the System,So that I can verify the Property of the User and required documents | 2 | 2
USID9 | Mortgage loan processing System | Approve Loan | As a Mortgage loan officer,I want to login to the Sstem,to aprove/reject the users request | 2 | 2
USID10 | Mortgage loan processing System | Settel Loan | As a loan Authoriser ,I want to login to the system,so that I can contact with the user and Communicate with them | 2 | 2

## Sprint TimeLines
Project Timelines
Sprint No | Title | Start Date | End Date | Duration | Effort - Total | Release Date | Review Date | Success Criteria | Remarks/Comments
1 | User Login and Loan Application and validation | 2018-05-15
2 | Admin Login and Approval/Rejection of Loans

## Sprint 1 Backlog
Sprint 1 BackLog
Task Id | Project | UserStory ID | User Story | Tasks | Status
T1 | Mortgage Loan Processing System | USID1 | As a non-registered user,I want to inquire for mortgage loan process,So that I can apply for a mortgage loan | Setup an inquire page for non-registered users
T2 | Mortgage Loan Processing System | USID2 | As a non-registered user,I want to sign up for mortgage loan process,So that I can apply for a mortgage loan | setup a signup page
T3 | Mortgage Loan Processing System | USID3 | As a registered user,I want to login to the system,so that I can apply mortgage loan | setup a login page
T4 | Mortgage Loan Processing System | USID3 | As a registered user,I want to login to the system,so that I can apply mortgage loan | Upload Documents
T5 | Mortgage Loan Processing System | USID6 | As a registered user,I want to login to the system,so that I can apply mortgage loan | change/forgot password,validate password
T6 | Mortgage Loan Processing System | USID3 | As a registered user,I want to login to the system,so that I can apply mortgage loan | Apply Loan,View Eligibility,Edit form,
T7 | Mortgage Loan Processing System | USID4 | As a registered user,I want to check my loan status,so that I can know my loan request is accepted or not | view track Loan application
T8 | Mortgage Loan Processing System | USID5 | As a registered user,I want to know how much loan amount is sanctioned/status also | show amount credited

## Sprint 2 Backlog
Sprint 2 BackLog
Task Id | Project | UserStory ID | User Story | Tasks | Status
T1 | Mortgage Loan Processing | USID7 | As a Mortgage Loan officer, I want to log in to the system,so that I can verify the documents provided by the user | cancel loan request
T2 | Mortgage Loan Processing | USID7 | As a Mortgage Loan officer, I want to log in to the system,so that I can verify the documents provided by the user | Validate Loan Application Sent By User
T3 | Mortgage Loan Processing | USID7 | As a Mortgage Loan officer, I want to log in to the system,so that I can verify the documents provided by the user | Sent Confirmation Email
T4 | Mortgage Loan Processing | USID7 | As a Mortgage Loan officer, I want to log in to the system,so that I can verify the documents provided by the user | view Loan applications reports sent by Loan Inspector
T5 | Mortgage Loan Processing | USID8 | As a Loan Inspector,I want to login to the System,So that I can verify the Property of the User and required documents | Access the mortgage property
T6 | Mortgage Loan Processing | USID9 | As a Mortgage loan officer,I want to login to the Sstem,to aprove/reject the users request | Approve/Reject Requests
T15 | Mortgage Loan Processing | USID6 | As a loan Authoriser ,I want to login to the system,so that I can contact with the user and Communicate with them | Interaction With The User For Loan Approval

## Sprint - 3
Sprint BackLog
Task Id | UseStory ID | Project | User Story | Tasks | Resource | Status
T1 | USID7 | Study Based application | User Registration | Create the wireframe for the story |  | closed
T2 | USID7 | Study Based application | User Registration | Create the user story document |  | closed
T3 | USID7 | Study Based application | User Registration | Create the Activity Diagram - flow for user story |  | closed
T4 | USID7 | Study Based application | User Registration | Implement the Data Repository Interfaces, Classes and Models |  | closed
T5 | USID7 | Study Based application | User Registration | Implement the Business Layer |  | closed
T6 | USID7 | Study Based application | User Registration | Write unit tests for the BusinessLayer methods added |  | Open
T7 | USID7 | Study Based application | User Registration | Create the controller for the UI defined |  | closed
T8 | USID7 | Study Based application | User Registration | Write unit tests for controller |  | Open
T9 | USID7 | Study Based application | User Registration | Create the HTML for the wireframe defined |  | closed
T10 | USID7 | Study Based application | User Registration | Integrate the controller and the view |  | closed
T11 | USID7 | Study Based application | User Registration | Write the Functional Test Cases for User Story |  | Open
T12 | USID7 | Study Based application | User Registration | Write the User Acceptance Test Cases for User Story |  | Open
T13 | USID7 | Study Based application | User Registration | Validate Non-Functional Requirements |  | Open
T14 | USID7 | Study Based application | User Registration | Integrate with the application |  | Open
T15 | USID7 | Study Based application | User Registration | CheckIn Code and Unit Tests |  | Open

## Resources IS
Resources Information
SL. No | Name | E - Mail ID | Contact #

## Miscalleneous
Project Repository Details |  |  | Configuration Details
SL. No | Name | Location | SL. No | Name | Location
1 | Code |  | 1 | Study Based application
2 | Documents |  | 2
3 | Design |  | 3
4 |  |  | 4
5 |  |  | 5
Software CheckList |  |  | Hardware Checklist
SL. No | Name | Category | SL. No | Name | Remarks
1 | SQL Server Management Studio | Database | 1
2 | Visual Studio2010 | Software | 2
3 |  |  | 3
4 |  |  | 4
5 |  |  | 5